## Sheet1
PROCESS PHASE | PROBLEM FRAMING | [7 empty] | DATA FRAMING |  |  |  | ANALYTICAL FRAMING
PROCESS STEP | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
| What is our strategic approach? | Who are the key customers? | What are the customer's broad objectives? | What is the customer doing today around the problem? | What are the customer's specific needs to improve current state &/ or fulfill stated objectives? | What are the model / output components that will determine a successful deliverable? | Have the components been stated back to the customer? What was the customer's response? | What data sources are available? | What data sources can be used to map to the output components? | How will those data sources be accessed? | What features will be extracted from each data source? | What are the qualities of the data that can be mapped to the KPIs? | What are the analytical methods to be used to estimate the KPIs? | Why are those analytical methods best suited to the task? | How will the chosen methods be evaluated? | Why will those evaluation methods be used? | How do the chosen evaluation methods align to the stated problem objectives?
TASK ORDER 1: Develop predictive capabilities of Future Year Defense Program (FYDP) forecast, in order to better anticipate future funding needs. | Direct staff work; identify gaps in current methodology & tools; set parameters on analytics & build; produce new reports for customer. 2-phase approach: 1) Develop predictive model 2) Monitor the performance of the budget | Tony Cifone; Analytics teams; Comptroller/ BFMs / Budget | Develop better way(s) to incorporate Enterprise & sub-command level data into yearly budget demands; make FYDP forecasts more predictive & dynamic | "Flat" estimates (e.g. last years budget + 5%); Results presented in an Excel / Tableau-type dashboard with highly aggregated & summarized data; Underlying drivers presented in a very basic way | A "dynamic" dashboard-type view that allows me to simulate what might happen in the future, around KPIs X Y Z | The current KPIs around budget & spend are better predicted; the key or suspected underlying drivers of budget increases are addressed (captured, quanitfied, & included in modeling & output) | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | ---
Date to complete
Step completed?
TASK ORDER 2: Initiate analytics collaboration with FRC, in order to mutually leverage analytical resources and expertise. | Consultative & direct staff work; identify collaboration areas for team backlog; prioritize projects by immediacy & value, & assess how / whether to engage on those projects. | Tony Cifone; Analytics teams; FRCs | Increase fleet readiness through the use of foundational maintenance data sources; integrate cost data & tie those costs to person-power. | Dependent on conversation with FRC AA&I team | --- | --- | --- | SDR; JDRS | --- | --- | --- | --- | --- | --- | --- | --- | ---
Date to complete
Step completed?
DATA THEMES |  |  | KEY TASK LIST | PROCESS STEP
|  |  | Understand the FYDP process | 3
|  |  | Obtain copies of reports, materials, outputs of current state & accompanying documentation for FYDP | 5